## Instructions
Client Onboarding Checklist for Independent Consultants – Excel & Google Sheets Template
1. Open the file in Excel or Google Sheets and enable editing.
2. Fill in the Overview tab to set project dates, budget, and status (calculated automatically).
3. Enter client details on the Client Info tab, then record the signed agreement on the Agreement tab.
4. Add required files on the Assets tab, list deliverables, and keep the Timeline, Payment, and Communication Log tabs updated weekly.
Works in Microsoft Excel, Google Sheets (File > Import) and Apple Numbers.
Blue header rows stay visible while you scroll. Totals sit under each table.
This template helps you organise your own numbers. It is not financial, tax or legal advice.

## Dashboard
Summary | Value
Overview: Total Budget
Payment Tracker: Amount
Payment Tracker: Overdue rows

## Overview
Project Name | Client | Start Date | End Date | Total Budget | Status
Website Redesign | Acme Corp | 2026-02-01 | 2026-03-01 | 3000 | Pending
SEO Audit | Beta LLC | 2026-02-10 | 2026-02-20 | 1200 | In-Progress
Brand Strategy | Gamma Inc | 2026-03-05 | 2026-04-05 | 2500 | Pending
TOTAL

## Payment Tracker
Invoice # | Amount | Due Date | Status | Paid Date | Balance | Overdue?
INV-001 | 1500 | 2026-02-15 | Unpaid
INV-002 | 800 | 2026-02-20 | Paid | 2026-02-18
INV-003 | 1200 | 2026-03-05 | Unpaid
TOTAL
Overdue rows
Formulas:
Overdue? = IF(AND(ISNUMBER([Due Date]),[Status]<>"Paid",[Due Date]<TODAY()),"OVERDUE","")

## Assets
Asset Type | Description | File Link | Owner | Due Date
Logo | High‑resolution logo files | https://example.com/logo.zip | Designer Jane | 2026-02-10
Content Calendar | Monthly content schedule | https://example.com/calendar.xlsx | Content Lead | 2026-02-12
Access Credentials | Admin login for CMS | https://example.com/creds.txt | IT Support | 2026-02-08
TOTAL

## Communication Log
Date | Medium | Summary | Action Items | Owner
2026-02-03 | Email | Sent project brief | Await client feedback | Consultant
2026-02-07 | Call | Discussed scope adjustments | Update agreement doc | Consultant
2026-02-12 | Video | Demo of initial mockups | Incorporate feedback | Designer
TOTAL