## Instructions
Design Agency Timeline Tracker – Google Sheets Template for Projects, Tasks & Real‑Time Progress (USD 14)
1. Open the Google Sheet and make a personal copy (File → Make a copy).
2. Fill in the **Projects** sheet with each client project; the Project ID can be any unique text.
3. Add tasks in **Deliverables**, linking each to its Project ID. Assign owners and due dates.
4. Team members log daily hours and notes in **Progress**; the Dashboard updates % Complete and total hours automatically.
5. If you track income or expenses, record them in the **Finance** sheet – the running balance updates automatically.
Works in Microsoft Excel, Google Sheets (File > Import) and Apple Numbers.
Blue header rows stay visible while you scroll. Totals sit under each table.
This template helps you organise your own numbers. It is not financial, tax or legal advice.

## Dashboard
Summary | Value
Projects: Days Left
Projects: Overdue rows
Deliverables: Time Spent (hrs)
Deliverables: Overdue rows
Progress: Hours
Finance: Amount

## Projects
Project ID | Project Name | Client | Start Date | Due Date | Owner | Priority | Status | Days Left | Overdue?
PRJ001 | Brand Refresh | Acme Corp | 2026-02-01 | 2026-03-15 | Lena | High | In Progress | 28
PRJ002 | Website Redesign | Beta Ltd | 2026-01-20 | 2026-04-01 | Marco | Med | Planned | 71
PRJ003 | Social Media Pack | Gamma Co | 2026-02-10 | 2026-02-28 | Aisha | Low | Completed | 0
TOTAL
Overdue rows
Formulas:
Overdue? = IF(AND(ISNUMBER([Due Date]),[Status]<>"Completed",[Due Date]<TODAY()),"OVERDUE","")

## Deliverables
Deliverable ID | Project ID | Task Description | Owner | Due Date | Status | Time Spent (hrs) | Overdue?
DLV001 | PRJ001 | Logo concepts | Lena | 2026-02-20 | Completed | 12
DLV002 | PRJ001 | Brand guidelines | Lena | 2026-03-10 | In Progress | 5
DLV003 | PRJ002 | Wireframe mockups | Marco | 2026-03-05 | Pending | 0
TOTAL
Overdue rows
Formulas:
Overdue? = IF(AND(ISNUMBER([Due Date]),[Status]<>"Completed",[Due Date]<TODAY()),"OVERDUE","")

## Progress
Date | Project ID | Deliverable ID | Hours | Notes
2026-02-12 | PRJ001 | DLV001 | 3 | Finalized logo sketches
2026-02-14 | PRJ001 | DLV002 | 2 | Started brand color palette
2026-02-15 | PRJ002 | DLV003 | 4 | Created initial wireframes
TOTAL

## Finance
Date | Project ID | Description | Amount | Balance
2026-02-05 | PRJ001 | Client deposit | 1500
2026-02-18 | PRJ001 | Stock image purchase | -120
2026-03-01 | PRJ002 | Initial invoice | 2000
TOTAL